12-month marketing execution plan

1. 12-Month Marketing Execution Plan (GranHub)

Quarter-by-quarter, month-by-month, with responsibilities, dependencies, and KPIs

Q1 — Foundation, Strategy, SEO Infrastructure (Months 1–3)

Month 1 — Strategy & Research

Objectives:

- Establish clear strategic direction

- Build marketing foundations

- Produce data-driven content roadmap

Key Tasks:

- Run SWOT workshop (Marketing Lead + Product Lead)

- Conduct 6–8 persona interviews (BA + Marketing)

- Complete competitor benchmarking matrix (BA)

- Export keyword list from SEMrush/Ahrefs (SEO specialist)

- Build keyword clusters + pillar topic map (BA + SEO)

- Draft Brand Messaging Framework

Deliverables:

- Persona cards

- JTBD canvas

- Competitor matrix

- 5-pillar content map

- Keyword cluster CSV

KPIs:

- None yet — foundation stage

Month 2 — Build SEO Machine

Objectives:

- Start producing scaled content

- Set up technical SEO

- Design content templates

Key Tasks:

- Create on-page templates (surfer guidelines, meta templates, CTA patterns)

- Establish internal linking rules

- Optimise site performance (Core Web Vitals)

- Begin producing Pillar 1 (Activities by Age)

- Draft 8–10 supporting posts

- Add schema markup

Deliverables:

- 1 pillar page draft

- 8 supporting article drafts

- Internal linking structure map

KPIs:

- Content velocity: 8 articles per month

- Site speed target: <2.5s load time

Month 3 — Activation & Email Infrastructure

Objectives:

- Convert visitors to sign-ups

- Improve retention & revisit rate

Key Tasks:

- Launch newsletter (Mailchimp/Klaviyo)

- Build welcome automation (3 emails)

- Create 6 social media templates

- Install GA4 event tracking

- Define activation metric (e.g., “Reads 3 articles + subscribes”)

- Publish Pillar 1

Deliverables:

- Newsletter automation

- Social media templates

- GA4 dashboard

KPIs:

- Sign-ups: 150 per month

- Activation rate target: 15%

Q2 — Community Launch & AI Assistive Features (Months 4–6)

Month 4 — Community MVP

Objectives:

- Begin user-generated content

- Increase loyalty

Key Tasks:

- Launch forum MVP (Discourse/Vanilla/BBPress)

- Add posting guidelines

- Begin moderator recruitment

- Add site-wide CTA banner to join community

- Publish Pillar 2 (Technology Help for Grandparents)

Deliverables:

- Forum MVP

- Moderation Policy & Workflow

- Pillar page + 8 supporting articles

KPIs:

- Forum sign-ups: 100

- Returning visitors: 18%

Month 5 — AI Summarisation & Accessibility

Objectives:

- Improve readability for senior users

- Reduce cognitive barriers

Key Tasks:

- Integrate AI summariser on articles

- Add “Read Aloud” text-to-speech feature

- Add glossary tooltips for tech terms

- A/B test article layout

- Publish Pillar 3 content drafts

Deliverables:

- AI summary feature

- Audio article player

- Accessibility update pack

KPIs:

- Avg. time on page ↑ by 20%

- Engagement (scroll depth > 50%) ↑ 15%

Month 6 — Scaling Content & SEO Authority

Objectives:

- Significantly increase organic traffic

Key Tasks:

- Publish Pillar 3

- Build 50 high-quality backlinks via partnerships

- Launch “Expert Contributors” programme

- Produce downloadable lead magnets (PDFs)

- Set up semantic site search

Deliverables:

- 3 pillar pages published

- 20–25 supporting articles

- 3 downloadable guides

KPIs:

- Organic visits: 10,000/month

- Sign-ups: 300/month

Q3 — Retention, Product-Led Growth & Personalisation (Months 7–9)

Month 7

- Launch personalised content feed (AI recommender)

- Add “Suggested for you” module

- Onboard 3–5 community ambassadors

Month 8

- Add quizzes + interactive tools (e.g., “Find activities by age”)

- Add trust badges & expert citations

Month 9

- Begin local UK content expansion

- Partner with councils, libraries, and activity centres

KPIs by end of Q3:

- Returning visitors: 25%

- Community DAU: 200

Q4 — Monetisation Experiments (Months 10–12)

Month 10–12

- Test premium experiences (printable packs, premium forum access)

- Launch affiliate partnerships (books, toys, devices)

- Explore sponsorship with AgeUK partners

Year-end KPIs:

- Organic visits: 25,000/month

- Email list: 5,000

- Active community: 1,000+ members